## _Initial Estimation (hidden)
EzBidn Mobile App - Estimation
Sr.No | Task Description | Comments | Design Hours | Mobile App Hours | API or Webservices Hours | Admin panel Hours
1 | UI Designs and Graphics module
| Design creation | Design creation will produce the Figma file. All elements will be sliced from the Figma file and will be used in the app | 18
| Design slicing | Design creation will produce the Figma file. All elements will be sliced from the Figma file and will be used in the app |  | 6
| Basic Navigational flow | Here we will design all screen to screen flow for the app |  | 8
| Design integration | Designs will be integrated in the app |  | 8
| Screen compatibility for different screen sizes | We will make screen compitable for all latest iphone and most common android screen sizes |  | 8
2 | Web services or API Creation | In this module, we will develop the APIs that serve as the communication bridge between the frontend, backend, and database. These APIs will handle data exchange and business logic. |  |  | 54
User Module
3 | Auth Module
| Onboarding module | We will design an Onboarding pages which helps user to understand flow of app |  | 4
| Registration using email address | User can send register them self using email, password and verification code send to thier email |  | 6
| Login to account | User can login using thier email address to thier account |  | 4
| Forget Password | User can recover thier password in case if forgets using this options |  | 4
| Explore app | User can see posts nearby them using this module and we will manage guest order here with this module |  | 8
| Login with apple | We will implement login with apple module in app only for iOS users |  | 6
| Login with google | We will implement login with google module in app |  | 6
4 | Profile Module
| Get and show profile details | User can see thier profile details under profile screen and they can manage settings here |  | 8
| Update profile | User can update their profile details like name, profile image, location and other details |  | 6
| Delete account | As per apple guideline we need to implement delete account feature if our app support user profile creation |  | 4
| Change password | User can change thier password using this option |  | 2
5 | Inmate Module
| Add inmate profile | User can search inmate details and we will fetch it from fedral API |  | 4
| Manage facility search | User can search facility and app will search it from database and show and once user select facility autofill information |  | 4
| List of inmates | User cna see list of thier added inmates |  | 6
| Manage inmate Profile | User can edit and delete inmate profiles |  | 6
6 | Order Module
| Add photos | User can select multiple photos and add to app and manage criteria like photo should be in JPG, PNG, HEIC formate, minimum resolution should be in 500*600 pixels and maximum size per photo should be 10MB |  | 8
| Show selected photos | User can see selected photos in grid in app and preview them if needed |  | 8
| Add captions | User can add captions to each photos which can be added to back of photo |  | 0 |  |  | We do not need this feature for now.
| Submit photos | User can submit photos and we will upload this photos to claude storage before submiting user need to accept photo upload content guideline |  | 8
| Manage performance target | Manage page load time and photo upload time and we will make this as fast as possible as it's also depends on server and hosting so |  | 18
| Select inmates | User can select inamtes after submiting photos |  | 2
| Review order | User can see order details like count of photos, inmate details and cost breackdown |  | 8
| Manage payments | User can select payment method and pay for order and once user payment confirm we will show payment confirmation screen with order number and send email for confirmation |  | 8
| Show order history | User cna see list of thier previous orders and they can aslo filter them by inmate or search |  | 8
| Show order detail | User can see order info, images annd other basic oreder details |  | 6
7 | Payment Module
| Integrate stripe library for payment | We will integrate stripe library for payment module |  | 6
| Show list of cards | We will show list of cards added by logged in user |  | 6
| Add card | User can add thier card we will use stripes secure methods to save card details |  | 4
| Delete card | User can delete thier card details from app |  | 4
| Google pay integration | We will integrate google pay payment method in app and this will only work with android phones |  | 18
| Apple pay integration | We will integrate apple pay payment method in app and this will only work with iOS phones |  | 14
8 | Notifications Module
| Implement firebase for notification | We will integrate firebase library for push notification and manage device push token |  | 4
| Send notification on order updates | We will send notification on order confirmation or refunds regarding order to user |  | 6
| Manage email notifications | We will send email notification for order updates to user |  | 6
9 | Testing of app | Manual testing will be conducted during this stage, where we will perform testing using basic test scenarios. This includes verifying core functionalities, checking UI elements, validating form inputs, and simulating typical user actions to ensure the application behaves as expected. Any issues identified during testing will be documented and addressed in this phase. |  | 28
Admin Module
10 | Set up Theme and login | We will set up admin panel templete, initial code and login for admin here |  |  |  | 8
11 | User Management
| List of user and enable/disable | We will show and allow admin to enable/disable accsess of user accounts, including subscription status and permissions |  |  |  | 8 |  | revenue , no of refunds, per month, matrix like a report
12 | Facility Management Module | Admin can add, upadte and deactive facilities in app and see list of them |  |  |  | 14
13 | Pricing Management Module | Admin can set price per photo and update shiping rates |  |  |  | 8
14 | Order Managemnet | Admin can add, update and delete orders and admin can review order and if any order violate content policy admin can cancel order which will triger refund logic |  |  |  | 18
15 | Testing of admin panel |  |  |  |  | 16
16 | Landing page Developement | We will design and deploy a landing page that clearly explains the app’s workflow and helps users easily understand how it works |  |  |  | 14
| Total Hours for Mobile app |  | 18 | 278 | 54 | 86 | 436 | Hours
Note:
We have considered flutter/react, PHP and MySQL for this project
We will use this API to search inmate using number: https://www.bop.gov/PublicInfo/execute/inmateloc?todo=query&output=json&inmateNumType=IRN&inmateNum=00123-871 We will use this API to search inmate using name: http://www.bop.gov/PublicInfo/execute/inmateloc?todo=query&output=json&nameFirst=john&nameLast=smith
We have not considered paypal and subscription in above estimation
We have not considered web app so we will add app links on landing page login and register will not supported on landing page
Please let us know if you would like us to include any other features as well, so we can update the scope accordingly, This helps avoid any confusion later.
We provide 30 days free support once app gets launched. After that we can discuss terms for app's maintnence
Server costing, app developer account costing and any other third party api costing has not been considered in above cost.
We have only considered phone app in this estimation
For the Apple Developer account, you’ll need to create an Organization account. Once that’s set up, you can invite us to join your account, and we can use it for development purposes. If you already have an Individual account, there are two options: 1. You can share the credentials with us for access. 2. Alternatively, you can log into your account in Xcode so we can upload the app to TestFlight.
We have only considered Potrait mode of app
We have not considerd light and dark mode of app.
All rights of source code will be yours

## Estimation
EzBidn Mobile App - Estimation
Sr.No | Task Description | Comments | Design Hours | Mobile App Hours | API or Webservices Hours | Admin panel Hours
1 | UI Designs and Graphics module
| Design creation | Design creation will produce the Figma file. All elements will be sliced from the Figma file and will be used in the app | 18
| Design slicing | Design creation will produce the Figma file. All elements will be sliced from the Figma file and will be used in the app |  | 6
| Basic Navigational flow | Here we will design all screen to screen flow for the app |  | 8
| Design integration | Designs will be integrated in the app |  | 8
| Screen compatibility for different screen sizes | We will make screen compitable for all latest iphone and most common android screen sizes |  | 8
2 | Web services or API Creation | In this module, we will develop the APIs that serve as the communication bridge between the frontend, backend, and database. These APIs will handle data exchange and business logic. |  |  | 54
User Module
3 | Auth Module
| Onboarding module | We will design an Onboarding pages which helps user to understand flow of app |  | 4
| Registration using email address | User can send register them self using email, password and verification code send to thier email |  | 6
| Login to account | User can login using thier email address to thier account |  | 4
| Forget Password | User can recover thier password in case if forgets using this options |  | 4
| Explore app | User can see posts nearby them using this module and we will manage guest order here with this module |  | 8
| Login with apple | We will implement login with apple module in app only for iOS users |  | 6
| Login with google | We will implement login with google module in app |  | 6
4 | Profile Module
| Get and show profile details | User can see thier profile details under profile screen and they can manage settings here |  | 8
| Update profile | User can update their profile details like name, profile image, location and other details |  | 6
| Delete account | As per apple guideline we need to implement delete account feature if our app support user profile creation |  | 4
| Change password | User can change thier password using this option |  | 2
5 | Inmate Module
| Add inmate profile | User can search inmate details and we will fetch it from fedral API |  | 4
| Manage facility search | User can search facility and app will search it from database and show and once user select facility autofill information |  | 4
| List of inmates | User can see list of thier added inmates |  | 6
| Manage inmate Profile | User can edit and delete inmate profiles |  | 6
6 | Order Module
| Add photos | User can select multiple photos and add to app and manage criteria like photo should be in JPG, PNG, HEIC formate, minimum resolution should be in 500*600 pixels and maximum size per photo should be 10MB |  | 8
| Show selected photos | User can see selected photos in grid in app and preview them if needed |  | 8
| Submit photos | User can submit photos and we will upload this photos to claude storage before submiting user need to accept photo upload content guideline |  | 8
| Manage performance target | Manage page load time and photo upload time and we will make this as fast as possible as it's also depends on server and hosting so |  | 18
| Select inmates | User can select inamtes after submiting photos |  | 2
| Review order | User can see order details like count of photos, inmate details and cost breackdown |  | 8
| Manage payments | User can select payment method and pay for order and once user payment confirm we will show payment confirmation screen with order number and send email for confirmation |  | 8
| Show order history | User cna see list of thier previous orders and they can aslo filter them by inmate or search |  | 8
| Show order detail | User can see order info, images annd other basic oreder details |  | 6
7 | Payment Module
| Integrate stripe library for payment | We will integrate stripe library for payment module |  | 6
| Show list of cards | We will show list of cards added by logged in user |  | 6
| Add card | User can add thier card we will use stripes secure methods to save card details |  | 4
| Delete card | User can delete thier card details from app |  | 4
| Google pay integration | We will integrate google pay payment method in app and this will only work with android phones |  | 18
| Apple pay integration | We will integrate apple pay payment method in app and this will only work with iOS phones |  | 14
8 | Notifications Module
| Implement firebase for notification | We will integrate firebase library for push notification and manage device push token |  | 4
| Send notification on order updates | We will send notification on order confirmation or refunds regarding order to user |  | 6
| Manage email notifications | We will send email notification for order updates to user |  | 6
9 | Testing of app | Manual testing will be conducted during this stage, where we will perform testing using basic test scenarios. This includes verifying core functionalities, checking UI elements, validating form inputs, and simulating typical user actions to ensure the application behaves as expected. Any issues identified during testing will be documented and addressed in this phase. |  | 28
Admin Module
10 | Set up Theme and login | We will set up admin panel templete, initial code and login for admin here |  |  |  | 8
11 | User Management
| List of user and enable/disable | We will show and allow admin to enable/disable accsess of user accounts, including subscription status and permissions |  |  |  | 8
12 | Manage analytics | We will show reports to admin, such as revenue, number of refunds, and a monthly revenue matrix |  |  |  | 16
13 | Pricing Management Module | Admin can set price per photo and update shiping rates |  |  |  | 8
14 | Order Managemnet | Admin can add, update and delete orders and admin can review order and if any order violate content policy admin can cancel order which will triger refund logic |  |  |  | 18
15 | Testing of admin panel |  |  |  |  | 16
16 | Landing page Developement | We will design and deploy a landing page that clearly explains the app’s workflow and helps users easily understand how it works |  |  |  | 14
| Total Hours for Mobile app |  | 18 | 278 | 54 | 88 | 438 | Hours
Note:
We have considered flutter/react, PHP and MySQL for this project
We will use this API to search inmate using number: https://www.bop.gov/PublicInfo/execute/inmateloc?todo=query&output=json&inmateNumType=IRN&inmateNum=00123-871 We will use this API to search inmate using name: http://www.bop.gov/PublicInfo/execute/inmateloc?todo=query&output=json&nameFirst=john&nameLast=smith
We have not considered paypal and subscription in above estimation
We have not considered web app so we will add app links on landing page login and register will not supported on landing page
Admin will manage orders manually from admin panel
Please let us know if you would like us to include any other features as well, so we can update the scope accordingly, This helps avoid any confusion later.
We provide 30 days free support once app gets launched. After that we can discuss terms for app's maintnence
Server costing, app developer account costing and any other third party api costing has not been considered in above cost.
We have only considered phone app in this estimation
For the Apple Developer account, you’ll need to create an Organization account. Once that’s set up, you can invite us to join your account, and we can use it for development purposes. If you already have an Individual account, there are two options: 1. You can share the credentials with us for access. 2. Alternatively, you can log into your account in Xcode so we can upload the app to TestFlight.
We have only considered Potrait mode of app
We have not considerd light and dark mode of app.
All rights of source code will be yours